## Tabelle1
Task: | Original Est | Current Est | Effort | Remaining | Responsible
Implement the Battle System
> Implement Core Mechanics (Fight, Run) | 15 | 20 | 4 | 16 | Keric, Wizany
> Implement Items | 10 | 15 | 0 | 15 | Keric, Wizany
> Implement "Switch" | 5 | 5 | 0 | 5 | Keric, Wizany
> Implement Shield Mechanic | 8 | 12 | 0 | 12 | Keric, Wizany
> Implement Soulbar Mechanic | 10 | 10 | 0 | 10 | Keric, Wizany
> Implement Combo/Partner Attack Mechanic | 12 | 12 | 0 | 12 | Keric, Wizany
Writing the Story | 6 | 6 | 2 | 4 | Keric, Wizany
Implement attacks | 15 | 15 | 12 | 3 | Keric, Wizany
Implement enemies | 15 | 15 | 0 | 15 | Keric, Wizany
Compose Music | 20 | 20 | 0 | 20 | Keric, Wizany
Compose Soundeffects | 15 | 15 | 0 | 15 | Keric, Wizany
Pixel Sprites
> Create Character and Enemy Battle-Sprites | 20 | 20 | 0 | 20 | Keric, Wizany
> Create GUI | 20 | 20 | 0 | 20 | Keric, Wizany
> Create Attack Sprites/Animation | 20 | 20 | 0 | 20 | Keric, Wizany
> Create Structure Sprites | 15 | 15 | 0 | 15 | Keric, Wizany