## Tabelle1
Initial
Open Story Points | Accomplished SP till now | Hours invested so far | Velocity so far
100 | 5 | 50 | 0.1
Product Burndown
Sprint | Planned Hours | SP change due to plan change | Accomplished story points in current sprint | Actual Hours | Open Story Points at Begin | Totally Accompl. SP at Begin | Actually accomplished SP at end. | Actual Hours so far at Begin | Open Story Points at End | Velocity (stpts / hour)
2017-04-27 | 18 |  | 0 | 20 | 100 | 0 | 0 | 0 | 100 | 0
2017-05-04 | 18 |  | 10 | 15 | 100 | 0 | 10 | 20 | 90 | 0.28571
2017-05-11 | 18 |  | 5 | 20 | 90 | 10 | 15 | 35 | 85 | 0.27273
2017-05-18 | 18 |  | 2 | 20 | 85 | 15 | 17 | 55 | 83 | 0.22667
2017-05-25 | 18 |  | 2 | 20 | 83 | 17 | 19 | 75 | 81 | 0.2
2017-06-01 | 18 |  | 5 | 20 | 81 | 19 | 24 | 95 | 76 | 0.2087
2017-06-08 | 18 |  |  |  | 76 | 24 | 24 | 115 | 72.2435 | 0.2087
2017-06-15 | 18 |  |  |  | 72.2435 | 24 | 24 | 115 | 68.487 | 0.2087
2017-06-22 | 18 |  |  |  | 68.487 | 24 | 24 | 115 | 64.7304 | 0.2087
2017-06-29 | 18 |  |  |  | 64.7304 | 24 | 24 | 115 | 60.9739 | 0.2087
2017-07-06 | 0 |  |  |  | 60.9739 | 24 | 24 | 115 | 60.9739 | 0.2087
2017-07-13 | 0 |  |  |  | 60.9739 | 24 | 24 | 115 | 60.9739 | 0.2087
2017-07-20 | 0 |  |  |  | 60.9739 | 24 | 24 | 115 | 60.9739 | 0.2087
2017-07-27 | 0 |  |  |  | 60.9739 | 24 | 24 | 115 | 60.9739 | 0.2087
2017-08-03 | 0 |  |  |  | 60.9739 | 24 | 24 | 115 | 60.9739 | 0.2087
2017-08-10 | 0 |  |  |  | 60.9739 | 24 | 24 | 115 | 60.9739 | 0.2087
2017-08-17 | 0 |  |  |  | 60.9739 | 24 | 24 | 115 | 60.9739 | 0.2087
2017-08-24 | 0 |  |  |  | 60.9739 | 24 | 24 | 115 | 60.9739 | 0.2087
2017-08-31 | 50 |  |  |  | 60.9739 | 24 | 24 | 115 | 50.5391 | 0.2087
2017-09-07 | 50 |  |  |  | 50.5391 | 24 | 24 | 115 | 40.1043 | 0.2087
2017-09-14 | 50 |  |  |  | 40.1043 | 24 | 24 | 115 | 29.6696 | 0.2087
2017-09-21 | 20 |  |  |  | 29.6696 | 24 | 24 | 115 | 25.4957 | 0.2087
2017-09-28 | 20 |  |  |  | 25.4957 | 24 | 24 | 115 | 21.3217 | 0.2087
2017-10-05 | 20 |  |  |  | 21.3217 | 24 | 24 | 115 | 17.1478 | 0.2087
2017-10-12 | 20 |  |  |  | 17.1478 | 24 | 24 | 115 | 12.9739 | 0.2087
2017-10-19 | 20 |  |  |  | 12.9739 | 24 | 24 | 115 | 8.8 | 0.2087
2017-10-26 | 20 |  |  |  | 8.8 | 24 | 24 | 115 | 4.6261 | 0.2087
2017-11-02 | 20 |  |  |  | 4.6261 | 24 | 24 | 115 | 0.45217 | 0.2087
2017-11-09 | 20 |  |  |  | 0.45217 | 24 | 24 | 115 | 0 | 0.2087
2017-11-16 | 20 |  |  |  | 0 | 24 | 24 | 115 | 0 | 0.2087
2017-11-23 | 20 |  |  |  | 0 | 24 | 24 | 115 | 0 | 0.2087
2017-11-30 | 20 |  |  |  | 0 | 24 | 24 | 115 | 0 | 0.2087
2017-12-07 | 20 |  |  |  | 0 | 24 | 24 | 115 | 0 | 0.2087
2017-12-14 | 20 |  |  |  | 0 | 24 | 24 | 115 | 0 | 0.2087
2017-12-21 | 20 |  |  |  | 0 | 24 | 24 | 115 | 0 | 0.2087
2017-12-28 | 20 |  |  |  | 0 | 24 | 24 | 115 | 0 | 0.2087
2018-01-04 | 20 |  |  |  | 0 | 24 | 24 | 115 | 0 | 0.2087
2018-01-11 | 20 |  |  |  | 0 | 24 | 24 | 115 | 0 | 0.2087
2018-01-18 | 20 |  |  |  | 0 | 24 | 24 | 115 | 0 | 0.2087
2018-01-25 | 20 |  |  |  | 0 | 24 | 24 | 115 | 0 | 0.2087
2018-02-01 | 20 |  |  |  | 0 | 24 | 24 | 115 | 0 | 0.2087
2018-02-08 | 20 |  |  |  | 0 | 24 | 24 | 115 | 0 | 0.2087
2018-02-15 | 20 |  |  |  | 0 | 24 | 24 | 115 | 0 | 0.2087
2018-02-22 | 20 |  |  |  | 0 | 24 | 24 | 115 | 0 | 0.2087
2018-03-01 | 20 |  |  |  | 0 | 24 | 24 | 115 | 0 | 0.2087
2018-03-08 | 20 |  |  |  | 0 | 24 | 24 | 115 | 0 | 0.2087
| 410 |  | 4 | 19.1667
Formulas:
Open Story Points = [Open Story Points, row above]+7